## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8A

## Slide 3
Modelling a Project
8A
You need to be able to represent the activities in a project in a way that makes the dependencies clear
A project is broken down into separate activities, usually labelled A, B, C, …
When one activity cannot start until another is completed, this is called a dependency
A precedence table (or dependence table) shows which activities must be completed before others are started
Only immediate dependence is shown in the table
The manufacture of a sofa involves the construction of a wooden frame which is then fitted with springs. The frame is then covered with padding and fabric. Cushions are cut out of the same fabric which must then be stitched and filled. The assembly of the sofa is completed by attaching the cushions. It is then inspected before being wrapped in a protective covering ready for shipping.
Represent the information above in a systematic way that makes any dependencies clear.
A Build wooden frame
B Cut out fabric for cushions
C Stitch and fill cushions
D Attach springs to wooden frame
E Cover frame
F Complete assembly
G Inspect
H Wrap
Activity
Depends on
A
–
B
–
C
B
D
A
E
D
F
C, E
G
F
H
G
E depends on D (and so on A), but only immediate dependence is shown
Both C and E must be completed before F may be started

## Slide 4
Modelling a Project
8A
Each row of a precedence table lists only the activities that come immediately before
If an activity is already implied by another entry in the column, leave it out
Read the information one sentence at a time and fill in the table as you go
The production of a new textbook may be broken down into activities A to G.
Activities A and B do not depend on any other activities.
Both activities C and D can only be started once A has been completed.
Activity E cannot be started until activity B has been completed and activity F cannot be started until activities C and E have been completed. Activity G can only begin once all other activities have been completed.
Draw a precedence table to represent this information.
Activity
Depends on
A
–
B
–
C
A
D
A
E
B
F
C, E
G
D, F
G depends on everything, but A, B, C and E are already implied by D and F

## Slide 5
Modelling a Project
8A
In an activity on arc network, activities are arcs and events are nodes
Each arc is labelled with its activity letter and an arrow shows its direction (use straight lines)
Nodes are numbered from 0, the source node, as they are added
The final node is the sink node
Draw in pencil: it often takes a couple of attempts to get the layout right
Draw an activity network for the precedence table given in Example 2.
Activity
Depends on
A
–
B
–
C
A
D
A
E
B
F
C, E
G
D, F
A
B
D
C
E
F
G
0
1
2
3
4
5
A and B depend on nothing, so they start at the source node, 0
C and D both start at node 1, the end of A
E starts at node 2, the end of B
F needs C and E, so their arcs meet at node 3
G needs D and F, so they meet at node 4. Node 5 is the sink