8B Dummy Activities

1.	Draw an activity network for this precedence table.

| Activity | Depends on |
| --- | --- |
| A | – |
| B | – |
| C | A, B |
| D | A |

Dummy activity:

Uniqueness: every activity must be uniquely represented in terms of its events, so

2.	This diagram shows part of an activity network. Event S depends on activities P, Q and R. Activities P and Q both start at event 6. Explain why P cannot also be drawn from event 6 to event 8, and show how a dummy can be used instead.

3.	Draw an activity network for this precedence table. Use exactly two dummies.

| Activity | Immediately preceding activities |
| --- | --- |
| A | – |
| B | A |
| C | A |
| D | A |
| E | B |
| F | B, C |
| G | D, F |
| H | D |
| I | G, H |