## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8B

## Slide 3
Dummy Activities
8B
You need to understand the use of dummy activities
Sometimes a network cannot show the dependencies using activity arcs alone
A dummy activity has no time or cost. Its sole purpose is to show dependencies between activities
A dummy is shown using a dotted line. The direction of its arrow is important
Draw an activity network for this precedence table.
Activity
Depends on
A
–
B
–
C
A, B
D
A
A
B
D
Dummy
C
0
1
2
3
A and B do not depend on anything: they start at the source node
D depends on A only, so it starts at node 1
C depends on both A and B. A dummy from node 1 to node 2 shows that A must also be finished before C
C starts at node 2

## Slide 4
Dummy Activities
8B
Every activity must be uniquely represented in terms of its events
This means there can be at most one activity between any two events
A dummy may be needed to make this happen
This diagram shows part of an activity network. Suppose that event S depends on activities P, Q and R, where P and Q both start at event 6. Show how the network should be drawn.
P
Q
R
6
8
If P were drawn from event 6 to event 8, then P and Q would both be the activity “from 6 to 8”. This is not allowed.
P
Q
R
Dummy
S
6
7
8
P ends at a new event 7 and a dummy joins event 7 to event 8, so every activity has its own pair of events.

## Slide 5
Dummy Activities
8B
Draw an activity network for this precedence table. Use exactly two dummies.
Activity
Immediately preceding
A
–
B
A
C
A
D
A
E
B
F
B, C
G
D, F
H
D
I
G, H
Look for an activity that depends on two things while another depends on only one of them
E needs only B, but F needs B and C
H needs only D, but G needs D and F
A
B
C
D
Dummy
E
F
Dummy
G
H
I
0
1
2
3
4
5
6
7
A starts at the source; B, C and D all follow A
E needs only B but F needs B and C: dummy from node 2 to node 3
H needs only D but G needs D and F: dummy from node 4 to node 5
I needs G and H; extend E to the sink so there is only one end point