## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8C

## Slide 3
Early and Late Event Times
8C
The length of time an activity takes is its duration, written in brackets on the arc
The early event time is the earliest time of arrival at the event allowing for the completion of all preceding activities
Early times are found with a forward pass: start at 0 at the source and work towards the sink
If several arcs arrive at an event, take the largest total
The activity durations are in hours. Find the early event time at each event (top box: early time, bottom box: late time).
A(2)
B(7)
C(4)
D(3)
E(2)
F(4)
G(1)
Dummy
0
2
Node after A: 0 + 2 = 2
7
Node after B: 0 + 7 = 7
6
Node after C: 2 + 4 = 6
7
Largest of 2 + 3 = 5 and 7 + 0 = 7, so 7
11
Sink: largest of 6 + 2 = 8, 7 + 4 = 11 and 7 + 1 = 8, so 11

## Slide 4
Early and Late Event Times
8C
The late event time is the latest time that the event can be left without extending the time needed for the project
Late times are found with a backward pass: start at the sink and work back to the source
At the sink the late time equals the early time
If several arcs leave an event, take the smallest value
The late time at the source is always 0
Now find the late event time at each event.
A(2)
B(7)
C(4)
D(3)
E(2)
F(4)
G(1)
Dummy
0
2
6
7
7
11
11
Sink: late time = early time = 11
9
Event 3: 11 − 2 = 9
7
Event 4: 11 − 4 = 7
7
Event 2: smallest of 11 − 1 = 10 and 7 − 0 = 7, so 7
4
Event 1: smallest of 9 − 4 = 5 and 7 − 3 = 4, so 4
0
Source: smallest of 4 − 2 = 2 and 7 − 7 = 0, so 0

## Slide 5
Early and Late Event Times
8C
To find an early event time, add each activity time to the early time at its start
Choose the largest result
A dummy (dotted line) has a duration of 0
The diagram shows part of an activity network.
Calculate the value of x.
D(5)
C(3)
2
7
9
x
Largest of:
2 + 5 = 7
7 + 3 = 10
9 + 0 = 9
x = 10

## Slide 6
Early and Late Event Times
8C
To find a late event time, subtract each activity time from the late time at its end
Choose the smallest result
For each event, the late time is greater than or equal to the early time: use this to check your answers
The diagram shows part of an activity network.
Calculate the value of y.
E(1)
F(3)
G(4)
4
y
5
6
9
10
8
8
Smallest of:
6 − 1 = 5
10 − 3 = 7
8 − 4 = 4
y = 4 (check: 4 ≥ early time 4)