## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8D

## Slide 3
Critical Activities
8D
An activity is critical if any increase in its duration results in a corresponding increase in the duration of the whole project
A path from the source to the sink which entirely follows critical activities is a critical path. It is the longest path in the network
At each event on a critical path the early event time equals the late event time
The diagram shows an activity network with early and late event times shown at the nodes. Identify the critical activities.
A(6)
B(3)
C(8)
D(7)
E(4)
F(5)
G(9)
H(8)
J(2)
I(8)
K(1)
L(7)
0
0
6
6
14
15
13
13
3
10
19
20
22
22
7
14
27
28
29
29
Critical events have early time = late time: 0, 6, 13, 22, 29
The critical activities are A, D, G and L
Check: 6 + 7 + 9 + 7 = 29, the time at the sink

## Slide 4
Critical Activities
8D
An activity connecting two critical events isn’t necessarily a critical activity
Check each one: early time at start + duration must equal the late time at the end
Part of an activity network is shown below including the early and late event times given in hours. Which are the critical activities?
F(8)
E(5)
G(6)
7
7
18
18
12
12
7 + 5 = 12 (critical)
12 + 6 = 18 (critical)
7 + 8 = 15 ≠ 18 (not critical)
The critical activities are E and G.
F is not critical even though it joins two critical events: its duration could increase by up to 3 hours without affecting the total time.

## Slide 5
Critical Activities
8D
A project can have more than one critical path
The total time is the same on each one
In the exam you may need to find all of the critical paths and identify all the critical activities
Find the critical paths in this activity network and identify the critical activities.
A(4)
B(5)
C(3)
D(3)
E(1)
F(4)
G(2)
H(5)
0
0
4
4
9
9
12
12
9
9
7
8
14
14
Path 1: A B D G (4 + 5 + 3 + 2 = 14)
Path 2: A B (dummy) H (4 + 5 + 0 + 5 = 14)
C is not critical: 4 + 3 = 7 but the late time is 8
The critical activities are A, B, D, G and H