## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8E

## Slide 3
The Float of an Activity
8E
The total float of an activity is the amount of time that its start may be delayed without affecting the duration of the project
total float = latest finish time − duration − earliest start time
Earliest start: early time at the start of the arc. Latest finish: late time at the end of the arc
The total float of any critical activity is 0
Determine the total float of each activity in this activity network.
A(3)
B(6)
C(4)
D(2)
E(1)
F(4)
G(5)
H(4)
0
0
3
3
9
9
11
11
9
12
7
11
16
16
Activity
LF − duration − ES
Total float
A
3 − 3 − 0
0
B
9 − 6 − 3
0
C
11 − 4 − 3
4
D
11 − 2 − 9
0
E
12 − 1 − 7
4
F
16 − 4 − 7
5
G
16 − 5 − 11
0
H
16 − 4 − 9
3
A, B, D and G are critical, so their float is 0