## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercises 8F and 8G

## Slide 3
Gantt Charts
8F
A Gantt (cascade) chart shows the range of possible start and finish times for all activities on one diagram
The scale shows elapsed time: the first hour is between 0 and 1, and so on
Critical activities go in a line at the top
Each other activity starts at its earliest start time; its total float is shown with a dotted box up to its latest finish time
Early and late event times are shown in hours at the nodes. Draw a Gantt chart to represent the project.
A(4)
B(3)
C(5)
D(2)
E(3)
F(2)
G(3)
H(2)
0
0
4
4
7
12
9
9
12
12
14
14
16
16
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
A
C
E
F
H
Critical activities A, C, E, F, H along the top
B
B: earliest start 4, duration 3, latest finish 12
D
D: earliest start 7, duration 2, latest finish 14
G
G: earliest start 9, duration 3, latest finish 16

## Slide 4
Gantt Charts
8F
A Gantt chart shows which activities must be happening at a given time and which may be happening
An activity must be happening if it is happening wherever it is placed within its float
Midday on day 10 is 9.5 on the elapsed time scale
The Gantt chart represents a project that must be completed within 25 days. Given that the project is on time,
a determine 3 activities that must be happening at midday on day 10.
b determine 1 additional activity that may be happening at midday on day 10.
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
A
C
G
J
B
D
E
F
H
I
a C is critical, so it must be happening
D (latest start 9) and E (latest start 7) are still happening at 9.5 even if they are delayed as long as possible
So C, D and E must be happening
b F may be happening: it has a total float of 5, so its start could be delayed until the start of day 14