## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8H

## Slide 3
Resource Histograms
8H
No worker can carry out more than one activity at the same time
Once a worker, or workers, have started an activity, they must complete it
Once they have finished an activity, they are immediately available to start another
A resource histogram shows the number of workers active at any time, assuming each activity starts at its earliest time
Here is the Gantt chart from question 2 of Exercise 8G.
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
A
C
F
H
B
D
E
G
The number of workers required for each activity is shown in this table.
Activity
A
B
C
D
E
F
G
H
Workers
2
1
1
2
1
1
2
1
Draw a resource histogram to show the number of workers required each day when each activity begins at its earliest time.
From end of day
To end of day
Activities
Workers
0
3
A, B
3
3
7
A, D, E
5
7
9
C, D, E
4
9
11
C, E, G
4
11
13
F, E, G
4
13
14
F, G
3
14
18
F
1
18
26
H
1

## Slide 4
Resource Histograms
8H
Write the letters in the squares to show which activities are happening on each day
An activity needing two workers takes two rows
Make sure there are no gaps in your resource histogram
Resource levelling: adjusting start times (within the float) to reduce the number of workers needed
0
2
4
6
8
10
12
14
16
18
20
22
24
26
0
1
2
3
4
5
6
Days
Workers
A
A
A
A
A
A
A
A
A
A
A
A
A
A
C
C
C
C
F
F
F
F
F
F
F
H
H
H
H
H
H
H
H
B
B
B
D
D
D
D
D
D
D
D
D
D
D
D
E
E
E
E
E
E
E
E
E
E
G
G
G
G
G
G
G
G
G
G
Five workers are needed between days 3 and 7
Activity E has a total float of 5. Delaying the start of E by 4 days means the project can be completed in the same time with only four workers.

## Slide 5
Resource Histograms
8H
The diagram shows a project modelled by an activity network. The number on each arc gives the time, in days, required to complete each activity. The number of workers needed for each activity is shown in the table. Each activity starts at its earliest possible time.
A(6)
B(3)
C(8)
E(7)
F(9)
G(8)
D(4)
H(8)
0
0
6
6
3
4
14
17
13
13
11
13
21
21
Activity
A
B
C
D
E
F
G
H
Workers
1
2
2
1
1
1
2
1
a Draw a resource histogram to show the number of workers required on each day, and state the total number of workers needed in this situation.
0
2
4
6
8
10
12
14
16
18
20
21
0
1
2
3
4
5
6
Days
Workers
A
A
A
A
A
A
E
E
E
E
E
E
E
H
H
H
H
H
H
H
H
Start with the critical path A E H along the base: one worker each
B
B
B
B
B
B
B starts at time 0 and needs two workers
F
F
F
F
F
F
F
F
F
G
G
G
G
G
G
G
G
G
G
G
G
G
G
G
G
F and G can start when B finishes at day 3
C
C
C
C
C
C
C
C
C
C
C
C
C
C
C
C
C can start when A finishes at day 6
D
D
D
D
D starts when C finishes at day 14
6 workers are required to complete the project in 21 days if each activity starts at its earliest time

## Slide 6
Resource Histograms
8H
The diagram shows a project modelled by an activity network. The number on each arc gives the time, in days, required to complete each activity. The number of workers needed for each activity is shown in the table. Each activity starts at its earliest possible time.
A(6)
B(3)
C(8)
E(7)
F(9)
G(8)
D(4)
H(8)
0
0
6
6
3
4
14
17
13
13
11
13
21
21
Activity
A
B
C
D
E
F
G
H
Workers
1
2
2
1
1
1
2
1
Only four workers are available. b Use resource levelling to show how the project can be completed with just 4 workers, and state the time required.
More than 4 workers are only needed between days 6 and 11, when C, E, F and G are active.
Activity
Total float
C
17 − 8 − 6 = 3
E
13 − 7 − 6 = 0
F
13 − 9 − 3 = 1
G
13 − 8 − 3 = 2
C has the largest float and needs 2 workers. Delay C by 5 days: it now starts at day 11 and D at day 19.
0
2
4
6
8
10
12
14
16
18
20
22
23
0
1
2
3
4
Days
Workers
A
A
A
A
A
A
E
E
E
E
E
E
E
H
H
H
H
H
H
H
H
B
B
B
B
B
B
F
F
F
F
F
F
F
F
F
G
G
G
G
G
G
G
G
G
G
G
G
G
G
G
G
C
C
C
C
C
C
C
C
C
C
C
C
C
C
C
C
D
D
D
D
C finishes 2 days after its late time, so with 4 workers the project takes 23 days