## Slide 1
Critical Path Analysis
Decision 1 Chapter 8
Westie's Workshop

## Slide 2
Teachings for Exercise 8I

## Slide 3
Scheduling Diagrams
8I
Scheduling is assigning workers to activities (assume each activity needs one worker)
Always use the first available worker
If there is a choice of activities for a worker, assign the one with the lowest late time
Shade any periods when a worker is inactive
The diagram shows a Gantt chart for a project. Schedule the activities to be completed in the critical time by the minimum number of workers.
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
A
C
G
J
B
D
E
F
H
I
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Worker 1
Worker 2
Worker 3
A
C
G
J
One worker does all the critical activities
B
D
E
Worker 2 does B then D. A third worker is needed to start E on time
F
Delay F as late as possible so worker 2 can do it after D
H
I
Start H as soon as possible and I as late as possible: worker 3 does both
Shade the idle time. 3 workers are needed

## Slide 4
Scheduling Diagrams
8I
The lower bound for the number of workers needed to complete a project within its critical time is the smallest integer greater than or equal to
(sum of all of the activity times) ÷ (critical time of the project)
It takes no account of how the activities overlap, so it does not guarantee that this number of workers is enough
Use the durations of the activities in the Gantt chart from the previous example to calculate a lower bound for the number of workers needed.
Activity
A
B
C
D
E
F
G
H
I
J
Total
Duration
8
6
8
7
11
10
5
3
4
4
66
Sum of the activity times = 66 days, critical time = 25 days
66 ÷ 25 = 2.64, so a lower bound is 3 workers
It is impossible to complete the project in 25 days with fewer than 3 workers. The scheduling diagram shows that 3 is enough.
Note: the textbook table uses I = 5 (total 67, and 67 ÷ 25 = 2.68), but the Gantt chart shows I lasting 4 days. Either way the lower bound is 3.

## Slide 5
Scheduling Diagrams
8I
If there are fewer workers than needed, work straight from the activity network
Check that all the activities an activity depends on are finished before you assign it
The activity network represents a project with a minimum time of 31 days. Use a scheduling diagram to find the new completion time given that only two workers are available.
A(8)
B(6)
C(9)
D(7)
F(4)
G(5)
I(5)
E(5)
H(8)
K(5)
J(5)
0
0
8
8
6
13
17
17
15
21
21
21
26
26
11
18
31
31
0
2
4
6
8
10
12
14
16
18
20
22
24
26
28
30
32
34
Worker 1
Worker 2
A
B
Day 0: worker 1 starts A, worker 2 starts B
E
Day 6: worker 2 is free first; E is the only activity available
C
Day 8: C (late time 17) before D (late time 21)
D
Day 11: worker 2 starts D
F
Day 17: worker 1 starts F
G
Day 18: worker 2 starts G
H
Day 21: worker 1 starts H
I
Day 23: worker 2 starts I (D and F are both finished)
K
Day 28: J must wait for H, so worker 2 starts K
J
Day 29: worker 1 starts J, finishing on day 34
The minimum time needed to complete the project using two workers is 34 days